## Community Contact Register
Community Contact Register - Website
Project Number: 2190128
Project Name: Locomotive Workshop, South Eveleigh
Enquiry Number | Date | Enquiry or complaint? | Details of enquiry or complaint | Follow Up
1 | 4.09.19 | Complaint | Saw cutting in the hall area. | Mirvac installed noise and vibration monitors (4 in total). It was also clarified that there was a lease agreement in place which allowed noisy works to be carried out between the hours of 7-10am Monday to Friday and 7-1pm Saturdays. Thresholds for noise and vibration are in place for works outside of these hours.
2 | 5.09.19 | Complaint | Saw cutting in the hall area. | Mirvac installed noise and vibration monitors (4 in total). It was also clarified that there was a lease agreement in place which allowed noisy works to be carried out between the hours of 7-10am Monday to Friday and 7-1pm Saturdays. Thresholds for noise and vibration are in place for works outside of these hours.
3 | 25.10.19 | Enquiry | Heritage tours | A community group wanted to organise a tour of the Locomotive Workshop for 30 people. Mirvac advised that heritage tours would resume late 2020.
4 | 07.01.20 | Enquiry | Purpose of the erection of the Tower Crane in Bay 4 | Clarification of the reason the Tower Crane was being installed, including faciliation of new fitout for commercial and retail tenants, as well as heritage exhibitions.
5 | 17.01.20 | Enquiry | Request for filming permit. | Filming permit issued.
6 | 22.01.20 | Enquiry | Request for tour of the Locomotive Workshop. | Advised that Locomotive Workshop under construction. Yerraingin rooftop sugested as an alternative.
7 | 29.01.20 | Enquiry | Ensure that the poor working conditions of Locomotive Workshop workers is reflected in heritage interpretation. | Confirmed that heritage interpretation would accurately reflect the poor working conditions in the Locomotive Workshops.
8 | 31.01.20 | Complaint | Request to extent the period of noisy works credit. | The asset management team are in conversation with Post Op to resolve this issue.
9 | 3.2.20 | Complaint | Leaking roof in Bay 14. | Mirvac coordinated repairs to rectify the issue.
10 | 21.5.2020 | Enquiry | Request to move the Ausgrid power outage date due to operational requirements | Meeting held on 25 May to discuss the use of a generator to ensure operational requirements can be met during power outage.
The project team hold weekly meetings with Post Op and Eveleigh Works to work through any issues and provide updates on the construction program. This is an effective way to minimise complaints and enquiries and ensure open lines of communications between key tenants that remain in the Locomotive Workshop during the redevelopment