## NSW
Residential Development
NEW SOUTH WALES
In Progress
| ACQUISITION/ AGREEMENT DATE | LOCATION | PROJECT VALUE | TOTAL LOTS2 | RELEASED | EXCHANGED | SETTLED | SETTLEMENT DATE3 |  | CURRENT PRICE RANGE |  | CONSTRUCTION | DESCRIPTION | OWNERSHIP STRUCTURE
PROPERTY |  |  | (INCL. GST) |  |  |  |  | FROM | TO | FROM | TO | PROGRESS4
The Avenue | Various (from 2012) | Schofields | 278.6 | 492 | 482 | 482 | 482 | FY14 | FY26 | 295000 | 819900 |  | MPC - Mix of land & housing | 100% Mirvac
Completed Stages |  |  | 174.9 | 232 | 232 | 232 | 232 | FY15 | FY20 | 312900 | 819900 | 100%
Balance of project |  |  | 103.7 | 260 | 250 | 250 | 250 | FY14 | FY26 | 295000 | 732500 | 91%
55 Coonara Avenue | 2020-05-01 | West Pennant Hills | TBC | 600 | 0 | 0 | 0 | FY25 | FY26 | TBC | TBC | 0% | Apartments and housing | 100% Mirvac
Cobbitty | 2021-12-23 | Cobbitty | TBC | 950 | 0 | 0 | 0 | FY24 | FY27 | TBC | TBC | 0% | MPC - Mix of land & housing | 100% Mirvac
Georges Cove | 2014-12-01 | Moorebank | 179.2 | 179 | 137 | 136 | 0 | FY23 | FY24 | 783000 | 1309000 | 24% | MPC - Medium density housing | PDA with Benedict Industries
Googong | 2011-12-01 | Googong | 1840.3 | 5488 | 2914 | 2881 | 2361 | FY14 | FY34 | 112000 | 660000 |  | MPC - Mix of land & housing | JV with PEET Limited
Completed Stages |  |  | 478.8 | 1942 | 1942 | 1942 | 1942 | FY14 | FY22 | 180000 | 470000 | 100%
Released Stages |  |  | 407 | 1059 | 972 | 939 | 419 | FY19 | FY32 | 310000 | 480000 | 59%
Future Stages |  |  | 954.5 | 2487 | 0 | 0 | 0 | FY24 | FY34 | 112000 | 660000 | 0%
Green Square | 2012-03-01 | Zetland | 2009.3 | 1,6125 | 637 | 553 | 476 | FY17 | FY28 | 498000 | 2970000 |  | Apartments with mixed use | PDA with Landcom / 100% Mirvac
Completed Stages1 |  |  | 508.6 | 477 | 477 | 476 | 476 | FY17 | FY20 | 498000 | 2080000 | 100%
Portman on the Park |  |  | 159.2 | 117 | 116 | 78 | 0 | FY23 | FY24 | 770000 | 2558000 | 15.6%
Portman House |  |  | 56.5 | 44 | 44 | 24 | 0 | FY23 | FY24 | 740000 | 3000000 | 15.6%
The Frederick |  |  | 207.3 | 151 | 151 | 39 | 0 | FY23 | FY24 | 720000 | 3995000 | 15.6%
Future Stages |  |  | 1077.7 | 823 | 0 | 0 | 0 | FY23 | FY28 | TBC | TBC | 0%
NINE by Mirvac | 2020-02-01 | Willoughby | 768.1 | 421 | 118 | 81 | 0 | FY23 | FY24 | $799,0009 | $4,975,0009 | 12% | Apartments with mixed use | 100% Mirvac
Pavilions | 2014-11-01 | Sydney Olympic Park | 354.4 | 3596 | 359 | 268 | 261 | FY20 | FY25 | 575000 | 2015000 | 100% | Apartments | PDA with Sydney Olympic Park Authority
Riverlands Milperra | 2019-10-01 | Milperra | TBC | TBC | 0 | 0 | 0 | FY23 | FY26 | TBC | TBC | 0% | MPC - Medium density housing | 100% Mirvac
St Leonards Square | 2015-06-01 | St Leonards | 814.7 | 5617 | 560 | 560 | 560 | FY20 | FY218 | 635000 | 5585000 |  | Apartments with mixed use | 100% Mirvac8
The William |  |  | 356.9 | 241 | 240 | 240 | 240 | FY20 | FY218 | 635000 | 2725000 | 100%
The Jackson |  |  | 457.8 | 320 | 320 | 320 | 320 | FY20 | FY21 | 640000 | 5585000 | 100%
The Langlee Waverley | 2020-12-01 | Waverley | 142.8 | 55 | 0 | 0 | 0 | FY23 | FY23 | TBC | TBC | 14.04% | Apartments | PDA with Eastern Suburbs Leagues Club Ltd
The Village | 2017-01-01 | Menangle | 188.4 | 379 | 130 | 113 | 0 | FY22 | FY25 | 444900 | 699900 | 15% | MPC - Mix of land & housing | PDA with SouWest Developments Pty Ltd
Proposed
| ACQUISITION/ AGREEMENT DATE |  | PROJECT VALUE | TOTAL LOTS2 |  |  |  | SETTLEMENT DATE3 |  |  |  |  | DESCRIPTION | OWNERSHIP STRUCTURE
PROPERTY |  | LOCATION | (INCL. GST) |  |  |  |  | FROM | TO
Marsden Park North | 2014-11-01 | Marsden Park | 280.2 | 547 |  |  |  | FY25 | FY28 |  |  |  | MPC - Mix of land & housing | PDA with MAC 1 MP Pty Ltd
Milperra, Western Sydney University Campus | 2019-08-01 | Milperra | 422.2 | 425 |  |  |  | FY25 | FY28 |  |  |  | MPC - Medium density housing | PDA with Western Sydney University
505 George Street | 2020-05-01 | Sydney | TBC | 260 |  |  |  | TBC | TBC |  |  |  | Apartments with mixed use | PDA with Coombes Property Group
1. Includes 1 retail lot, expected to settle FY24.
2. Indicative only and subject to change. Final lot number will depend on planning outcomes, development and construction decisions as well as market demand and conditions, including COVID-19 uncertainties.
3. Settlement dates may vary as circumstances change, such as planning outcomes, development and construction decisions as well as market demand and conditions, including COVID-19 uncertainties.
4. Construction progress as a percentage of cost, which includes land subdivision but not land acquisition.
5. Includes retail lots.
6. Excludes affordable housing lots to be delivered to Sydney Olympic Park Authority and Build to Rent lots.
7. Includes 34 retail/commercial strata lots. Retail lots expected to settle in the future.
8. Ownership was JV with Ping An through Aug-21, all residential lots settled prior to structure change.
9. Price range relates to released lots and is not indicative of future releases.

## QLD
Residential Development
QUEENSLAND
In Progress
| ACQUISITION/ AGREEMENT DATE | LOCATION | PROJECT VALUE | TOTAL LOTS2 | RELEASED | EXCHANGED | SETTLED | SETTLEMENT DATE3 |  | CURRENT PRICE RANGE |  | CONSTRUCTION | DESCRIPTION | OWNERSHIP STRUCTURE
PROPERTY |  |  | (INCL. GST) |  |  |  |  | FROM | TO | FROM | TO | PROGRESS4
Ascot Green | 2015-09-01 | Ascot | 875.3 | 964 | 173 | 172 | 166 | FY18 | FY31 | 460000 | 3200000 |  | Apartments | PDA with Brisbane Racing Club
Ascot House |  |  | 86.3 | 90 | 90 | 90 | 90 | FY18 | FY21 | 460000 | 3200000 | 100%
Tulloch House |  |  | 77.8 | 83 | 83 | 82 | 76 | FY22 | FY22 | 460000 | 2120000 | 100%
Charlton House |  |  | 124.8 | 115 | 0 | 0 | 0 | FY24 | FY24 | 495000 | 2200000 | 0%
Future Stages |  |  | 586.4 | 676 | 0 | 0 | 0 | FY25 | FY31 | 495000 | 2200000 | 0%
Ashford | 2017-03-01 | Everton Park | 86.6 | 124 | 118 | 118 | 39 | FY21 | FY23 | 489000 | 845000 |  | MPC - Land, Medium Density Housing | 100% Mirvac
Completed Stages |  |  | 22.8 | 39 | 39 | 39 | 39 | FY21 | FY21 | 489000 | 674000 | 100%
Released Stages |  |  | 63.8 | 85 | 79 | 79 | 0 | FY22 | FY23 | 630000 | 845000 | 37%
Everleigh | 2016-02-01 | Greenbank | 845.9 | 3456 | 591 | 494 | 461 | FY19 | FY35 | 145000 | 295000 |  | MPC - Land lots | 100% Mirvac
Released Stages |  |  | 215.3 | 926 | 591 | 494 | 461 | FY19 | FY25 | 145000 | 295000 | 68%
Future Stages |  |  | 630.6 | 2530 | 0 | 0 | 0 | FY24 | FY35 | 210000 | 275000 | 0%
Gainsborough Greens | 2006-10-01 | Pimpama | 514.8 | 2017 | 1992 | 1963 | 1940 | FY11 | FY23 | 143000 | 655000 |  | MPC - Mix of land & housing | 100% Mirvac
Completed Stages |  |  | 357.4 | 1408 | 1408 | 1408 | 1408 | FY11 | FY21 | 143000 | 480000 | 100%
Released Stages |  |  | 157.4 | 609 | 584 | 555 | 532 | FY12 | FY23 | 210000 | 655000 | 91%
Waterfront Sky | Apr 081 | Newstead | 513.7 | 420 | 135 | 133 | 0 | FY24 | FY27 | 382000 | 5390000 |  | Apartments | 100% Mirvac
Quay |  |  | 196.9 | 135 | 135 | 133 | 0 | FY24 | FY24 | 382000 | 5390000 | 6%
Isle |  |  | 185.2 | 135 | 0 | 0 | 0 | FY26 | FY26 | 465000 | 4600000 | 0%
Future Stages |  |  | 131.6 | 150 | 0 | 0 | 0 | FY27 | FY27 | 465000 | 4600000 | 0%
1. Agreement date relates to Waterfront Newstead precinct.
2. Indicative only and subject to change. Final lot number will depend on planning outcomes, development and construction decisions as well as market demand and conditions, including COVID-19 uncertainties.
3. Settlement dates may vary as circumstances change, such as planning outcomes, development and construction decisions as well as market demand and conditions, including COVID-19 uncertainties.
4. Construction progress as a percentage of cost, which includes land subdivision but not land acquisition.

## VIC
Residential Development
VICTORIA
In Progress
| ACQUISITION/ AGREEMENT DATE | LOCATION | PROJECT VALUE | TOTAL LOTS1 | RELEASED | EXCHANGED | SETTLED | SETTLEMENT DATE2 |  | CURRENT PRICE RANGE |  | CONSTRUCTION | DESCRIPTION | OWNERSHIP STRUCTURE
PROPERTY |  |  | (INCL. GST) |  |  |  |  | FROM | TO | FROM | TO | PROGRESS3
699 Park Street | 2021-06-01 | Brunswick | TBC | 218 | 0 | 0 | 0 | FY25 | FY25 | TBC | TBC | 0% | Apartments | 100% Mirvac
Olivine | 2012-06-01 | Donnybrook | 1565.5 | 4497 | 1061 | 1055 | 741 | FY18 | FY38 | 127000 | 449000 |  | MPC - Mix of land & housing | Combination of balance sheet and DMA with Boral
Completed Stages |  |  | 151.7 | 450 | 450 | 450 | 450 | FY18 | FY22 | 127000 | 449000 | 100%
Released Stages |  |  | 163.4 | 612 | 611 | 605 | 291 | FY19 | FY24 | 132000 | 427000 | 60%
Future Stages |  |  | 1250.4 | 3435 | 0 | 0 | 0 | FY23 | FY38 | TBC | TBC | 5%
Smiths Lane | 2011-11-01 | Clyde North | 1262.9 | 3178 | 1056 | 1016 | 505 | FY19 | FY29 | 173000 | 653000 |  | MPC - Mix of land & housing | 100% Mirvac
Completed Stages |  |  | 53 | 227 | 227 | 227 | 227 | FY19 | FY22 | 173000 | 459000 | 100%
Released Stages |  |  | 331.4 | 934 | 829 | 789 | 278 | FY19 | FY26 | 210000 | 653000 | 70%
Future Stages |  |  | 878.5 | 2017 | 0 | 0 | 0 | FY23 | FY29 | TBC | TBC | 2%
The Eastbourne | 2012-12-01 | East Melbourne | 460.3 | 258 | 258 | 258 | 257 | FY19 | FY22 | 500000 | 14000000 | 100% | Apartments | PDA with Freemasons
The Fabric | 2020-07-01 | Altona North | 422 | 573 | 124 | 110 | 0 | FY22 | FY28 | 475000 | 1250000 |  | MPC - Mix of housing and apartments | 100% Mirvac
Released Stages |  |  | 113.2 | 124 | 124 | 110 | 0 | FY22 | FY24 | 660000 | 1250000 | 30%
Future Stages (MPC) |  |  | 145.9 | 157 | 0 | 0 | 0 | FY24 | FY25 | 680000 | 1186000 | 0%
Future Stages (apartments) |  |  | 162.9 | 292 | 0 | 0 | 0 | FY25 | FY28 | 475000 | 640000 | 0%
Tullamore | 2015-07-01 | Doncaster | 882.2 | 914 | 903 | 846 | 771 | FY16 | FY24 | 380000 | 2595000 |  | MPC - Mix of land, housing & medium density housing | 100% Mirvac
Completed Stages |  |  | 360.7 | 352 | 352 | 352 | 352 | FY16 | FY22 | 540000 | 1950000 | 100%
Released Stages |  |  | 267.2 | 233 | 222 | 216 | 184 | FY17 | FY234 | 980000 | 2595000 | 86%
Apartments Building A (Phoenix) |  |  | 92.9 | 134 | 134 | 134 | 134 | FY19 | FY21 | 380000 | 1519000 | 100%
Apartments Building B (Folia) |  |  | 79.6 | 102 | 102 | 101 | 101 | FY21 | FY22 | 395000 | 1835000 | 100%
Apartments Building C (Forme) |  |  | 81.8 | 93 | 93 | 43 | 0 | FY23 | FY24 | 415000 | 2500000 | 10%
Wantirna South | 2019-06-01 | Wantirna South | 1357.4 | 1717 | 0 | 0 | 0 | FY26 | FY35 | TBC | TBC | 0% | MPC - Mix of land, housing & medium density housing | PDA with Boral
Waverley Park | 2001-12-01 | Mulgrave | 784.4 | 1319 | 1317 | 1317 | 1303 | FY04 | FY23 | 225000 | 1525000 |  | MPC - Housing | 100% Mirvac
Completed Stages |  |  | 750.4 | 1283 | 1283 | 1283 | 1283 | FY04 | FY22 | 225000 | 1525000 | 100%
Released Stages |  |  | 34 | 36 | 34 | 34 | 20 | FY18 | FY23 | 520000 | 1200000 | 90%
Woodlea | 2006-11-01 | Rockbank | 1958.5 | 6584 | 4370 | 4365 | 3742 | FY16 | FY33 | 135500 | 1088888 |  | MPC - Mix of land & housing | 50% Mirvac 50% Jayaland Corporation
Completed Stages |  |  | 775.7 | 3005 | 3005 | 3005 | 3005 | FY16 | FY22 | 135500 | 1088888 | 100%
Released Stages |  |  | 496.1 | 1488 | 1365 | 1360 | 737 | FY20 | FY25 | 203000 | 588000 | 60%
Future Stages |  |  | 686.7 | 2091 | 0 | 0 | 0 | FY23 | FY33 | TBC | TBC | 0%
Yarra's Edge |  | Docklands | 1557.7 | 1526 | 1128 | 991 | 957 | FY05 | FY27 | 120000 | 7280000 |  | Apartments (and townhouses) | 100% Mirvac
Completed Stages | 2011-04-01 |  | 714.4 | 664 | 664 | 664 | 664 | FY13 | FY20 | 500000 | 6000000 | 100%
Marina Berths | 2004-03-01 |  | 18.1 | 149 | 149 | 116 | 116 | FY05 | FY26 | 120000 | 285000 | 100%
Voyager - Tower 11 | 2016-10-01 |  | 303.5 | 315 | 315 | 211 | 177 | FY22 | FY25 | 475000 | 2000000 | 100%
Future Stages | - |  | 521.7 | 398 | 0 | 0 | 0 | FY25 | FY27 | 415000 | 7280000 | 0%
1. Indicative only and subject to change. Final lot number will depend on planning outcomes, development and construction decisions as well as market demand and conditions, including COVID-19 uncertainties.
2. Settlement dates may vary as circumstances change, such as planning outcomes, development and construction decisions as well as market demand and conditions, including COVID-19 uncertainties.
3. Construction progress as a percentage of cost, which includes land subdivision but not land acquisition.
4. Retail lots expected to settle in the future.

## WA
Residential Development
WESTERN AUSTRALIA
In Progress
| ACQUISITION/ AGREEMENT DATE | LOCATION | PROJECT VALUE | TOTAL LOTS1 | RELEASED | EXCHANGED | SETTLED | SETTLEMENT DATE2 |  | CURRENT PRICE RANGE |  | CONSTRUCTION | DESCRIPTION | OWNERSHIP STRUCTURE
PROPERTY |  |  | (INCL. GST) |  |  |  |  | FROM | TO | FROM | TO | PROGRESS3
Claremont, Corner Graylands Road & KYLE WAY | 2015-01-01 | Claremont | 152.5 | 233 | 233 | 232 | 232 | FY19 | FY22 | 399000 | 1495000 |  | Apartments | 100% Mirvac
Grandstand |  |  | 91.3 | 142 | 142 | 141 | 141 | FY19 | FY22 | 399000 | 1165000 | 100%
Reserve |  |  | 61.2 | 91 | 91 | 91 | 91 | FY19 | FY21 | 495000 | 1495000 | 100%
Henley Brook, PARK STREET | 2018-11-01 | Henley Brook | 156.6 | 628 | 102 | 60 | 56 | FY22 | FY26 | 185000 | 325000 |  | MPC - Land lots | 100% Mirvac
Released Stages |  |  | 30.6 | 116 | 102 | 60 | 56 | FY22 | FY22 | 185000 | 319000 | 85%
Future Stages |  |  | 126 | 512 | 0 | 0 | 0 | FY23 | FY26 | 185000 | 325000 | 0%
Iluma Private Estate, Marshall Road | 2014-12-01 | Bennett Springs | 163.8 | 625 | 513 | 441 | 431 | FY18 | FY24 | 125000 | 349000 |  | MPC - Land lots | 100% Mirvac
Completed Stages |  |  | 31.8 | 118 | 118 | 118 | 118 | FY18 | FY21 | 219000 | 329000 | 100%
Released Stages |  |  | 104.9 | 401 | 395 | 323 | 313 | FY18 | FY24 | 125000 | 349000 | 86%
Future Stages |  |  | 27.1 | 106 | 0 | 0 | 0 | FY23 | FY24 | 225000 | 329000 | 0%
Madox, Nicholson Road | 2016-02-01 | Piara Waters | 118.7 | 402 | 359 | 283 | 262 | FY18 | FY24 | 135000 | 385000 |  | MPC - Land lots | 100% Mirvac
Completed Stages |  |  | 27 | 88 | 88 | 88 | 88 | FY18 | FY23 | 165000 | 385000 | 100%
Future Stages |  |  | 91.7 | 314 | 271 | 195 | 174 | FY18 | FY24 | 135000 | 375000 | 70%
ONE71 Baldivis, Baldivis Road | 2013-12-01 | Baldivis | 73.9 | 414 | 271 | 237 | 237 | FY16 | FY28 | 139000 | 268000 |  | MPC - Land lots | 100% Mirvac
Completed Stages |  |  | 24.5 | 126 | 126 | 126 | 126 | FY16 | FY22 | 165000 | 268000 | 100%
Released Stages |  |  | 28 | 161 | 145 | 111 | 111 | FY16 | FY28 | 139000 | 246000 | 75%
Future Stages |  |  | 21.4 | 127 | 0 | 0 | 0 | FY24 | FY28 | 139000 | 205000 | 0%
Osprey Waters, Bridgewater Boulevard | 2013-12-01 | Mandurah | 84.2 | 462 | 462 | 445 | 444 | FY14 | FY22 | 109000 | 278000 |  | MPC - Land lots | 100% Mirvac
Completed Stages |  |  | 58.2 | 325 | 325 | 325 | 325 | FY14 | FY19 | 109000 | 239000 | 100%
Released Stages |  |  | 26 | 137 | 137 | 120 | 119 | FY14 | FY22 | 147000 | 278000 | 100%
The Peninsula, The Circus | 2003-02-01 | Burswood | 838.2 | 779 | 531 | 459 | 443 | FY07 | FY26 | 350000 | 13395000 |  | Apartments, Medium Density & Land Lots | 100% Mirvac
Completed Stages |  |  | 490.8 | 443 | 443 | 443 | 443 | FY07 | FY22 | 385000 | 13395000 | 100%
Ador |  |  | 95.6 | 88 | 88 | 16 | 0 | FY24 | FY25 | 485000 | 2775000 | 0%
Future Stages |  |  | 251.8 | 248 | 0 | 0 | 0 | FY24 | FY26 | 350000 | 3000000 | 0%
1. Indicative only and subject to change. Final lot number will depend on planning outcomes, development and construction decisions as well as market demand and conditions, including COVID-19 uncertainties.
2. Settlement dates may vary as circumstances change, such as planning outcomes, development and construction decisions as well as market demand and conditions, including COVID-19 uncertainties.
3. Construction progress as a percentage of cost, which includes land subdivision but not land acquisition.